PROJECT CHARTER

GENERAL PROJECT INFORMATION

- Project Name: Online Cab Service System

- Project Manager: Tharindu Fernando

- Project Sponsor: Chamila Karunaratne

- Email: tharindu.fernando@cabservices.lk

- Phone: +94 77 456 7890

- Organizational Unit(s): Development, Operations, and Customer Support

- Expected Start Date: 02/01/2024

- Expected Completion Date: 08/01/2024

PROJECT OVERVIEW

Problem or Issue
There is a need for a reliable and user-friendly cab service platform in Sri Lanka to address the increasing demand for on-demand transportation.

Purpose of Project
To develop an online cab service system that connects customers with nearby drivers, offering convenient and affordable transportation services while supporting local drivers.

Business Case
The online cab service industry is growing rapidly, and Sri Lanka lacks a comprehensive, locally focused platform. This system aims to capture the market by offering competitive rates, easy-to-use interfaces, and efficient service.

Goals/Metrics

- Onboard 1,000 drivers within 3 months of launch.

- Achieve 50,000 app downloads within the first 6 months.

- Maintain an average trip rating of 4.5 stars or higher.

Expected Deliverables

- A fully functional online cab service app with driver and customer interfaces, real-time tracking, payment integration, and a rating system.

PROJECT SCOPE

Within Scope

- Design and development of the app for Android and iOS.

- Integration of location tracking and payment systems.

- Onboarding of drivers in Colombo and Gampaha districts.

- Marketing and promotional campaigns.

Outside of Scope

- Recruitment of drivers (drivers must register independently).

- Maintenance of vehicles (responsibility of the drivers).

TENTATIVE SCHEDULE

| Key Milestone | Start Date | Finish Date |
| --- | --- | --- |
| Form Project Team / Preliminary Review / Scope | 02/01/2024 | 02/15/2024 |
| Finalize Project Plan / Charter / Kick Off | 02/16/2024 | 02/28/2024 |
| Define Phase | 03/01/2024 | 03/31/2024 |
| Development Phase | 04/01/2024 | 06/15/2024 |
| Testing and Feedback | 06/16/2024 | 07/15/2024 |
| App Launch | 08/01/2024 | 08/01/2024 |

RESOURCES

Project Team

- Tharindu Fernando - Project Manager

- Nuwan Silva - Lead Developer

- Iresha Weerasinghe - Marketing Lead

- Kasun Bandara - Operations Lead

- Amali Perera - QA Engineer

Support Resources

- IT Support, Legal Advisors, Content Writers

Special Needs

- Access to GPS services and mapping APIs.

- Collaboration with local driver associations.

COSTS

| Cost Type | Vendor/Labor Names | Rate | Quantity | Amount |
| --- | --- | --- | --- | --- |
| Development | App Lanka Pvt Ltd | $60/hr | 600 hrs | $36,000 |
| Marketing | AdBoost Sri Lanka | $35/hr | 300 hrs | $10,500 |
| Testing | QA Hub Pvt Ltd | $25/hr | 200 hrs | $5,000 |

Total Costs: $51,500

BENEFITS AND CUSTOMERS

Process Owner
Tharindu Fernando - Project Manager

Key Stakeholders

- Chamila Karunaratne - Project Sponsor

- Local Drivers

- App Development Team

Final Customer
Commuters in Colombo and surrounding areas looking for on-demand cab services.

Expected Benefits

- Enhanced convenience for passengers.

- Increased income opportunities for drivers.

- Improved urban mobility and reduced traffic congestion.

RISKS, CONSTRAINTS, AND ASSUMPTIONS

Risks

- Delays in app development or driver onboarding.

- Technical issues during peak usage times.

Constraints

- Limited budget for marketing.

- High competition from existing platforms.

Assumptions

- Drivers will register promptly upon launch.

- Customers will adopt the platform quickly due to competitive pricing.

Prepared By: Tharindu Fernando
Title: Project Manager
Date: 12/30/2024

Let me know if you need this converted into a document!